## User Story
S. No | As a <<type of user>> | I want <<some goal>> | so that <<reason>> | Date introduced | Date considered for implementation | Developer Responsible | Current Status
1 | Admin | Create an accounts for physicians | There must be an administrator (or administrators) for the EMR component who will create the accounts for the physicians. | 2015-01-31 |  | Yufan Xue | In Progress
2 | Admin | Add an account for physicians | An administrator can only add or delete an account for a physician or for another administrator. | 2015-01-31 |  |  | Not Started
3 | Admin | Delete an account for physicians | An administrator can only add or delete an account for a physician or for another administrator. | 2015-01-31 |  |  | Not Started
4 | Admin | Check with Administrative component | Admin can create or delete a physician's account | 2015-02-08 |  |  | Not Started
5 | Physician | Login | physician can access the system and perform admin related tasks | 2015-02-01 | 2015-02-15 | JingBo | In Progress
6 | Physician | Add an EMR | Pysician can add an EMR for a patient There should be at most only one EMR per patient. A physician can create an EMR for a patient if and only if the physician is the primary care of the patient. | 2015-01-31 |  |  | Not Started
7 | Physician | View an EMR | By default, a physician can search view all EMRs of his/her patients. To view the EMR of another patient, the physician should have been given access rights by the primary care of the corresponding physician. | 2015-02-01 |  |  | Not Started
8 | Physician | Search an EMR | Search an EMR or a collection of EMRs. | 2015-02-02 |  |  | Not Started
9 | Physician | Add a new trasncription | Add a new trasncription when a patient sees a physician | 2015-02-03 |  |  | Not Started
10 | Physician | Update EMR of a patient | Updating an EMR should not modify or delete any existing transcription. Instead, it may change the patient's preferences | 2015-02-04 |  |  | Not Started
11 | Physician | Add acceess rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. | 2015-02-05 |  |  | Not Started
12 | Physician | Delete access rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. | 2015-02-06 |  |  | Not Started
13 | Physician | Create prescription for a patient | The patient needs this to buy medicine from pharmacy. The prescription should be stored along with the transcription. | 2015-02-07 |  |  | Not Started

## Sprints
S.No. | User Story index | Task | Date introduced | Date considered for implementation | Date completed | Developer responsible for | Current Status
1 | 4 | Set up the database | 2015-01-31 |  |  | Yufan xue | In Progress
2 | 4 | Set up web interface |  |  |  |  | Not Started
3 | 4 | Develop DB access methods |  |  |  |  | Not Started
4 | 4 | Develop GUI and front end control |  |  |  |  | Not Started
5 | 4 | Develop back end service |  |  |  |  | Not Started
6 | 4 | Integerate front end and back end |  |  |  |  | Not Started
7 | 4 | Test login code for physician |  |  |  |  | Not Started
8 | 5 | Set up the database | 2015-01-31 |  |  |  | Not Started
9 | 5 | Set up web interface |  |  |  |  | Not Started
10 | 5 | Develop DB access methods |  |  |  |  | Not Started
11 | 5 | Develop GUI and front end control |  |  |  |  | Not Started
12 | 5 | Develop back end service |  |  |  |  | Not Started
13 | 5 | Integerate front end and back end |  |  |  |  | Not Started
14 | 5 | Test add EMR code for physician |  |  |  |  | Not Started
15 | 6 | Set up the database | 2015-01-31 |  |  |  | Not Started
16 | 6 | Set up web interface |  |  |  |  | Not Started
17 | 6 | Develop DB access methods |  |  |  |  | Not Started
18 | 6 | Develop GUI and front end control |  |  |  |  | Not Started
19 | 6 | Develop back end service |  |  |  |  | Not Started
20 | 6 | Integerate front end and back end |  |  |  |  | Not Started
21 | 6 | Test view EMR code for physician |  |  |  |  | Not Started
22 | 7 | Set up the database | 2015-01-31 |  |  |  | Not Started
23 | 7 | Set up web interface |  |  |  |  | Not Started
24 | 7 | Develop DB access methods |  |  |  |  | Not Started
25 | 7 | Develop GUI and front end control |  |  |  |  | Not Started
26 | 7 | Develop back end service |  |  |  |  | Not Started
27 | 7 | Integerate front end and back end |  |  |  |  | Not Started
28 | 7 | Test search EMR code for physician |  |  |  |  | Not Started
29 | 8 | Set up the database | 2015-01-31 |  |  |  | Not Started
30 | 8 | Set up web interface |  |  |  |  | Not Started
31 | 8 | Develop DB access methods |  |  |  |  | Not Started
32 | 8 | Develop GUI and front end control |  |  |  |  | Not Started
33 | 8 | Develop back end service |  |  |  |  | Not Started
34 | 8 | Integerate front end and back end |  |  |  |  | Not Started
35 | 8 | Test add transcription code for physician |  |  |  |  | Not Started
36 | 9 | Set up the database | 2015-01-31 |  |  |  | Not Started
37 | 9 | Set up web interface |  |  |  |  | Not Started
38 | 9 | Develop DB access methods |  |  |  |  | Not Started
39 | 9 | Develop GUI and front end control |  |  |  |  | Not Started
40 | 9 | Develop back end service |  |  |  |  | Not Started
41 | 9 | Integerate front end and back end |  |  |  |  | Not Started
42 | 9 | Test update EMR code for physician |  |  |  |  | Not Started
43 | 10 | Set up the database | 2015-01-31 |  |  |  | Not Started
44 | 10 | Set up web interface |  |  |  |  | Not Started
45 | 10 | Develop DB access methods |  |  |  |  | Not Started
46 | 10 | Develop GUI and front end control |  |  |  |  | Not Started
47 | 10 | Develop back end service |  |  |  |  | Not Started
48 | 10 | Integerate front end and back end |  |  |  |  | Not Started
49 | 10 | Test add acceess rights for another physician to a patient's EMR code for physician |  |  |  |  | Not Started
50 | 11 | Set up the database | 2015-01-31 |  |  |  | Not Started
51 | 11 | Set up web interface |  |  |  |  | Not Started
52 | 11 | Develop DB access methods |  |  |  |  | Not Started
53 | 11 | Develop GUI and front end control |  |  |  |  | Not Started
54 | 11 | Develop back end service |  |  |  |  | Not Started
55 | 11 | Integerate front end and back end |  |  |  |  | Not Started
56 | 11 | Test delete acceess rights for another physician to a patient's EMR code for physician |  |  |  |  | Not Started
57 | 12 | Set up the database | 2015-01-31 |  |  |  | Not Started
58 | 12 | Set up web interface |  |  |  |  | Not Started
59 | 12 | Develop DB access methods |  |  |  |  | Not Started
60 | 12 | Develop GUI and front end control |  |  |  |  | Not Started
61 | 12 | Develop back end service |  |  |  |  | Not Started
62 | 12 | Integerate front end and back end |  |  |  |  | Not Started
63 | 12 | Test Create prescription for a patient code for physician |  |  |  |  | Not Started
64 | 13 | Set up the database | 2015-01-31 |  |  |  | Not Started
65 | 13 | Set up web interface |  |  |  |  | Not Started
66 | 13 | Develop DB access methods |  |  |  |  | Not Started
67 | 13 | Develop GUI and front end control |  |  |  |  | Not Started
68 | 13 | Develop back end service |  |  |  |  | Not Started
69 | 13 | Integerate front end and back end |  |  |  |  | Not Started
70 | 13 | Test Create prescription for a patient code for physician |  |  |  |  | Not Started